## 023-C-DAT-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 2 | The | In comparison with FEED datasheet, the Absorber operating pressure has been increased, therefore, please revise/confirm the maximum hydrogen pressure.
2 | Call-out | 3 | Ali Kadhem | It is noted that the hold-up time in the FEED datasheet was calculated based on the maximum liquid flowrate including a 20% overdesign, however, in this datasheet it seems that it is based on the maximum operating liquid flowrate i.e. without 20% overdesign. Please confirm and provide the rational for this change.