## 023-C-DAT-00005-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Ali Kadhem | The datasheet of 023V0002 to be kept on hold, as the design of 1HRU Amine Absorber Inlet Gas – Separation of Hydrocarbon Condensate is under review between TTSJV and Owner. Please refer to the Owner’s email issued through the Project Mailbox, dated 2 August 2018.
2 | Call-out | 2 | Ahmed Bucheeri | Either to add the material/spec in the table or to add the comment of using SA 516 GR 60N & SA 285 GR C as per feed sheet
3 | Call-out | 2 | Ahmed Bucheeri | To be GR LF2 as per feed sheet