## 023-C-DAT-00007-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | General Comment: This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template and cover page shall be used.
2 | Cloud+ | 1 | MAK | NO. 1 HYDROGEN RECOVERY UNIT
3 | Call-out | 2 | Ali Hasan | 478 psig is the design as per IBD P&ID. Please modify the pressure in the P&ID if 490 psig is confirmed.
4 | Call-out | 2 | Ahmed Bucheeri | Clarify the selection of SS316L instead of SS316 as stated in feed data sheet
5 | Call-out | 2 | Rashed Almudahka | JV to furnish the applicable spares to this equipment.
6 | Call-out | 2 | Rashed Almudahka | latest edition of ASME VIII Div.1 to be followed.
7 | Call-out | 2 | Ali Kadhem | Note 19 specified for the Relief Valve, however, it appears to be not applicable for “Net Flux Rate”. TTSJV to add a new note (reward for clarity) for “Net Flux Rate”.
8 | Call-out | 2 | Rashed Almudahka | Note no.10 is irrelevant to equipment support. please modify.
9 | Call-out | 2 | Ali Kadhem | The flux rate in the Bapco’s existing 1HCU PSA Product Filter 76V7673 is about 5300 gpm/ft2 (gas flowrate - standard condition), in comparison with 10,000 gpm/ft2 specified in this datasheet, therefore, TTSJV to consider revising the flux rate spec for 023V0006.
10 | Call-out | 3 | Rashed Almudahka | add (... as per BMPS-A3 clause 7.2.)
11 | Call-out | 3 | Rashed Almudahka | provide the basis of deleting note no. 12 & 13.