## 023-C-GAD-00003-002-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | 023 - NO. 1 HYDROGEN RECOVERY UNIT
2 | Text Box | 1 | MAK | General Comment: All the texts in drawings shall be searchable and in UPPERCASE. Text fonts and styles shall be as per BMPS-A8.
3 | Call-out | 1 | Ali Kadhem | Please refer to our comment provided also in the datasheet of 023V0004 issued by TTSJV (BMP-ROC-TRI-00374): “Amine carryover is a likely scenario for this vessel, therefore, as an alternate case, specific gravity of amine (1.04) should also be specified.”
4 | Call-out | 1 | Ali Kadhem | Please refer to our comment provided also in the datasheet of 023V0004 issued by TTSJV (BMP-ROC-TRI-00374): “This vessel is feeding the PSA unit and therefore effective mist elimination is critical. TTSJV to consider a higher mist elimination arrangement. ”