## 023-E-DAT-00004-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Call-out | 2 | Ali Kadhem | It is noted that the flowrate of the purge gas has been changed from 92,715 lb/hr in the FEED datasheet to 92,817 lb/hr in this datasheet. Purge gas flowrate of 92,817 lb/hr is also specified in the IBD issue of PFD H&MB. However, in the latest revised Basis of Design document issued by TTSJV, the purge gas flowrate is specified as 93,252.6 lb/hr. Since we do not have the latest revised 1HRU H&MB, TTSJV shall ensure that the data (including the flowrate) in this datasheet is consistent with the latest revised 1HRU H&MB available with TTSJV and the Basis of Design document.
3 | Call-out | 4 | Rashed Almudahka | Provide the basis of changing the material grade
4 | Call-out | 4 | Rashed Almudahka | provide the specification and grade of tie rods and spacers material
5 | Call-out | 6 | Rashed Almudahka | Full RT is required for shell side. please modify