## 023-E-DAT-00005-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Call-out | 2 | Ali Kadhem | As per PFD (IBD) H&MB is 0.32 cP. Please check and confirm.
3 | Call-out | 2 | Ali Kadhem | As per PFD (IBD) H&MB is 0.762Btu/lb.F Please check and confirm.
4 | Call-out | 2 | Ali Kadhem | As per PFD (IBD) H&MB is 0.801Btu/lb.F Please check and confirm.
5 | Call-out | 2 | Ali Kadhem | As per PFD (IBD) H&MB is 0.805Btu/lb.F Please check and confirm.
6 | Call-out | 2 | Ali Kadhem | As per PFD (IBD) H&MB is 44.7 lb/ft3. Please check and confirm.
7 | Text Box | 2 | Ali Kadhem | Since this cooler has been added during EPC, TTSJV to ensure that the cooling water requirement for this cooler is updated in the utility consumption summary and is considered for the design of the cooling tower.
8 | Call-out | 2 | Ali Kadhem | Since we do not have the latest revised 1HRU H&MB, TTSJV shall ensure that the data (including the flowrate) in this datasheet is consistent with the latest revised 1HRU H&MB available with TTSJV.
9 | Call-out | 3 | Rashed Almudahka | RV set pressure on tube discharge line is higher than tube design pressure. please clarify
10 | Call-out | 4 | Rashed Almudahka | Fill in the uncompleted data