## 023-E-DAT-00006-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Call-out | 2 | Ali Kadhem | It is noted that the flowrate of the compressed gas and the cooling water has been changed compared to the FEED datasheets and the IBD issue of PFD H&MB. Since we do not have the latest revised 1HRU H&MB, TTSJV shall ensure that the data (including the flowrate) in this datasheet is consistent with the latest revised 1HRU H&MB available with TTSJV and the revised Basis of Design Document.
3 | Text Box | 2 | Ali Kadhem | It is noted that the flowrate of the compressed gas and the cooling water has been changed compared to the FEED datasheets and the IBD issue of PFD H&MB. Since we do not have the latest revised 1HRU H&MB, TTSJV shall ensure that the data (including the flowrate) in this datasheet is consistent with the latest revised 1HRU H&MB available with TTSJV and the revised Basis of Design.
4 | Call-out | 3 | Rashed Almudahka | RV set pressure on tube discharge line is 465psig. please clarify
5 | Call-out | 4 | Rashed Almudahka | Provide the basis of changing the material grade, CA & thickness
6 | Call-out | 6 | Rashed Almudahka | Provide the basis of removing note 15 from FEED data sheet.