## 023-E-GAD-00005-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | ALL THE TEXT IN THIS DRAWING SHALL SEARCHABLE. TEXT FONTS AND STYLES SHALL BE AS PER BMPS-A8
2 | Text Box | 1 | rob.urban | The Owner does not have the means to verify the calculations undertaken by the Contractor and can only verify certain data included within the report from available documentation. It is the Contractor’s responsibility to ensure correctness and accuracy of the data in line with the terms of the Contract.
3 | Call-out | 1 | Rashed Almudahka | Channel cover material is SA266Gr2 as per EPC data sheet. please modify
4 | Cloud+ | 1 | MAK | 023 - NO. 1 HYDROGEN RECOVERY UNIT
5 | Call-out | 1 | Rashed Almudahka | RV set pressure. in tube discharge lines, is 465psig which is higher than tubes' design pressure. please clarify
6 | Cloud+ | 1 | MAK | 5
7 | Cloud+ | 1 | MAK | Fill in EX and PN nos.
8 | Call-out | 1 | Rashed Almudahka | full RT is required for shell and tube sides. please modify