## 023-G-DAT-00001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | rob.urban | Comments to be discussed
2 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
3 | Call-out | 2 | Ali Kadhem | It is noted that the discharge pressure is revised in comparison with FEED datasheet. Please confirm this is based on the EPC latest hydraulic calculation.
4 | Call-out | 2 | Ali Kadhem | It is noted that the flowrate (rated/normal/minimum) has been revised in comparison with FEED datasheet. Please confirm that the “Flowrate” and “Liquid Characteristics” are consistent with the revised 1HRU H&MB, because we do not have yet the latest revised revision.
5 | Text Box | 4 | Isamu | FEED DS opted for SS piping, flanges and socket welding and these shall prevail per Owner decision. Please comply and correct even though tubing is mentioned in BMPS-G9
6 | Text Box | 5 | Isamu | Please comply with FEED DS requirement for witnessed inspection and test. Changing to observed is rejected without Owner prior approval on selected test and selected pump on case by case basis. There is no "Observe" level of inspection in the ITB (BMPS-G-50309) and "witness" must be retained on the data sheet in line with the definition of the ITP. Also Refer to BMPS-B11 / BMPS-G1 / API 610 parag 3.64 and 3.38 for definitions of witness.
7 | Call-out | 7 | Ali Kadhem | As per BMPS-G2 6.1.8 add a note as follow: "NPSH (required) shall not be more than 55% of NPSH (available). Refer to project specification BMPS-G2 for further information.”
8 | Text Box | 7 | AliRedha Malalla | 20. PUMP & M/SEAL OEM SHALL PROVIDE MEASURED STUFFING BOX PRESSURE.