## 023-G-DAT-00002-001-RB-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | General Comments: - Use the latest datasheet template that is part of the Homogenization Procedure. - Always use the long description of Unit names unless the space doesn't permit.
2 | Text Box | 1 | Ravi Kumar | OPEN COMMENT IN RESOLUTION SHEET FOR REV A DATASHEET TO BE CLOSED
3 | Cloud+ | 2 | MAK | 023 - NO. 1 HYDROGEN RECOVERY UNIT
4 | Call-out | 5 | Ahmed Bucheeri | To fill the required NDE as per table no.14 and inspection class 3
5 | Cloud+ | 7 | MAK | 023V0003