## 023-S-DAT-00001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 2 | Ali Kadhem | Utilities/Catalyst/ Chemical consumption is part of the guarantees.
2 | Callout | 2 | Syed Ahmed | please review this temperature
3 | Call-out | 2 | Ali Kadhem | To ensure homogenization and with reference to note no.3 of the datasheet of the Hydrogen Plant PSA 099U0001, the following to be added to the performance guarantees: - Minimum purge gas pressure of 5 psig, and maximum pressure fluctuation of + 2psi. - variation in flowrate (less than 3%) and composition of purge gas (variation in wobbe index less tan 5%).
4 | Call-out | 2 | Ali Kadhem | As we do not have the latest 1HRU H&MB, please ensure the feed gas composition/flowrate is based on the latest revised 1HRU H&MB. Note 31 to be updated accordingly, if required.
5 | Call-out | 4 | Ali Kadhem | To ensure homogenization and with reference to note no.13 of the datasheet of the Hydrogen Plant PSA 099U0001, note no.5 of this datasheet to be written as follow: "Steam out design condition is -10 psig at 300ÂºF as per 7.1 of BMPS-A3. Supplier shall confirm necessity of steam out condition and compliance with the design condition as applicable."
6 | Call-out | 4 | Mahdi Ali | Do not use FEED numbers.
7 | Text Box | 4 | Ali Hasan | Please add the following Note: Vendor to advise the recovery ratio, purified gas composition and conditions, and offgas flowrate and composition for the design case (off-gas Amine Absorber 23C0001 is out of service).
8 | Text Box | 4 | Mahdi Ali | 023-A-PFD-00001-001/2/3
9 | Call-out | 4 | Ali Kadhem | Note 12: the PSA Purge Gas Drum(s) is specialised activity. Sizing and supply of the vessel(s) must be in the scope of the PSA package vendor. This is also in line with the Hydrogen Plant PSA 099U0001 and the existing units.
10 | Call-out | 4 | Ali Kadhem | Add to note no.13: "and guarantees."
11 | Call-out | 4 | Rashed Almudahka | Provide the basis of deleting note 5
12 | Callout | 5 | Syed Ahmed | In addition, all PSA interconnecting pipes and control valves inside the package shall be easy for removal for maintenance.
13 | Call-out | 5 | Ali Abbas | Vendor to advise/recommend the current trend in controlling the PSA through a stand alone dual redundant PLC or the logic can be developed in the DCS.
14 | Call-out | 5 | Ali Kadhem | Note 21: The following to be added: "or shutdown of any other upstream process units feeding 1HRU,"
15 | Call-out | 5 | Rashed Almudahka | provide the basis of deleting note 24.
16 | Call-out | 5 | Ali Kadhem | TTSJV to prepare a table showing each PSA feed stream considering the shutdown of each upstream unit. This will help the vendor to evaluate.
17 | Text Box | 5 | Ali Kadhem | To ensure homogenization and with reference to the note no.2 and no.6 in the datasheet of the Hydrogen Plant PSA 099U0001, the following notes to be added to this datasheet: 1. Automatic reduced bed operation mode is required. Supplier shall advise the number of reduced bed steps and corresponding capacity, recovery, and purge gas composition/heating value at each step. 2. Supplier shall include the following in the scope: (a) Unit inlet and outlet isolation valves. (b) Manual isolation for each adsorber and each valve (for maintenance). (c) Shutdown instrumentation.
18 | Text Box | 5 | Ali Kadhem | The P&ID sheet of the PSA package to be shared with the PSA package vendor for information and review.
19 | Call-out | 5 | Ali Abbas | Detailed control, sequence and shutdown narratives and flow charts to be included in the proposal.
20 | Call-out | 5 | Ali Abbas | Instrumentation design to follow our project BMPSs requirements