## 050-A-EQL-55001-001-R0
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | General Comments: - This is not the latest document template. For all documents, use the latest document template that is part of the Homogenisation Procedure. - For A3 documents in landscape mode, use A3 landscape oriented cover page and so for A4. Portrait cover page shall be used for portrait oriented document.
2 | Cloud+ | 1 | Mohamed Ayyash | Project number missing
3 | Cloud+ | 1 | Mohamed Ayyash | Unit name/number missing
4 | Text Box | 3 | David.Jimenez | ?
5 | Cloud+ | 3 | Yousif Ahmadi | Add material for Tanks (CS)
6 | Cloud+ | 3 | MAK | Change to: 050OMG5001
7 | Callout | 3 | Fernando.Perez | Criticality Rating to be included
8 | Callout | 3 | Fernando.Perez | Material of Construction required for Shaft & Impeller can be included
9 | Call-out | 3 | Abdulaziz | Mixers and motors position shall be revised and corrected accordingly
10 | Callout | 3 | Fernando.Perez | MotorTAG
11 | Callout | 3 | Berik.Nurbolatov | N/A
12 | Call-out | 3 | Abdulaziz | Painting responsibility shall be indicated
13 | Text Box | 3 | David.Jimenez | PID location?