## 050-A-EQL-55001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 3 | Adnan Alothman | 010M0031A | Done | Y
2 | Text Box | 3 | Adnan Alothman | 010M0031B | Done | Y
3 | Text Box | 3 | Adnan Alothman | 010P0031A | Done | Y
4 | Text Box | 3 | Adnan Alothman | 010P0031A | Done | Y
5 | Text Box | 3 | Adnan Alothman | 010P0031B | Done | Y
6 | Text Box | 3 | Adnan Alothman | 010P0031B | Done | Y
7 | Text Box | 3 | Adnan Alothman | 018M0038A | Done | Y
8 | Text Box | 3 | Adnan Alothman | 018M0038B | Done | Y
9 | Text Box | 3 | Adnan Alothman | 018P0038A | Done | Y
10 | Text Box | 4 | Adnan Alothman | 018P0038A | Done | Y
11 | Text Box | 3 | Adnan Alothman | 018P0038B | Done | Y
12 | Text Box | 4 | Adnan Alothman | 018P0038B | Done | Y
13 | Text Box | 3 | Adnan Alothman | 019DS0001A | Tag number designated according to consecutive number for the c019 unit | N
14 | Text Box | 3 | Adnan Alothman | 019DS0001B | Tag number designated according to consecutive number for the c019 unit | N
15 | Text Box | 3 | Adnan Alothman | 019M0029C | Done | Y
16 | Text Box | 4 | Adnan Alothman | 019P0029A | Done | Y
17 | Text Box | 4 | Adnan Alothman | 019P0029A | Done | Y
18 | Text Box | 4 | Adnan Alothman | 019P0029A | Done | Y
19 | Text Box | 4 | Adnan Alothman | 019P0029B | Done | Y
20 | Text Box | 4 | Adnan Alothman | 019P0029B | Done | Y
21 | Text Box | 4 | Adnan Alothman | 019P0029B | Done | Y
22 | Text Box | 3 | Adnan Alothman | 019P0029C | Done | Y
23 | Text Box | 4 | Adnan Alothman | 019P0029C | Done | Y
24 | Text Box | 3 | Adnan Alothman | 019T0029A | Done | Y
25 | Text Box | 4 | Adnan Alothman | 019T0029A | Done | Y
26 | Text Box | 3 | Adnan Alothman | 019T0029B | Done | Y
27 | Text Box | 4 | Adnan Alothman | 019T0029B | Done | Y
28 | Text Box | 3 | Adnan Alothman | 021DS0002A | Done | Y
29 | Text Box | 3 | Adnan Alothman | 021DS0002B | Done | Y
30 | Text Box | 3 | Adnan Alothman | 021M0013C | Done | Y
31 | Text Box | 3 | Adnan Alothman | 021P0013A | Done | Y
32 | Text Box | 4 | Adnan Alothman | 021P0013A | Done | Y
33 | Text Box | 4 | Adnan Alothman | 021P0013A | Done | Y
34 | Text Box | 3 | Adnan Alothman | 021P0013B | Done | Y
35 | Text Box | 4 | Adnan Alothman | 021P0013B | Done | Y
36 | Text Box | 4 | Adnan Alothman | 021P0013B | Done | Y
37 | Text Box | 3 | Adnan Alothman | 021P0013C | Done | Y
38 | Text Box | 3 | Adnan Alothman | 021P0013C | Done | Y
39 | Text Box | 3 | Adnan Alothman | 021T0013A | Done | Y
40 | Text Box | 4 | Adnan Alothman | 021T0013A | Done | Y
41 | Text Box | 3 | Adnan Alothman | 021T0013B | Done | Y
42 | Text Box | 4 | Adnan Alothman | 021T0013B | Done | Y
43 | Text Box | 3 | Adnan Alothman | 050D1001 | Done | Y
44 | Text Box | 3 | Adnan Alothman | 050D1002 | Done | Y
45 | Text Box | 3 | Adnan Alothman | 050D1003 | Done | Y
46 | Text Box | 3 | Adnan Alothman | 050D1004 | Done | Y
47 | Text Box | 3 | Adnan Alothman | 050M5075A | Done | Y
48 | Text Box | 3 | Adnan Alothman | 050M5075B | Done | Y
49 | Text Box | 3 | Adnan Alothman | 050M5076A | Done | Y
50 | Text Box | 3 | Adnan Alothman | 050M5076B | Done | Y
51 | Text Box | 3 | Adnan Alothman | 050MX5010 | Done | Y
52 | Text Box | 3 | Adnan Alothman | 050MX5011A | Done | Y
53 | Text Box | 3 | Adnan Alothman | 050MX5011B | Done | Y
54 | Text Box | 3 | Adnan Alothman | 050MX5012A | Done | Y
55 | Text Box | 3 | Adnan Alothman | 050MX5012B | Done | Y
56 | Text Box | 3 | Adnan Alothman | 050MX5013A | Done | Y
57 | Text Box | 3 | Adnan Alothman | 050MX5013B | Done | Y
58 | Text Box | 3 | Adnan Alothman | 050MX5014A | Done | Y
59 | Text Box | 3 | Adnan Alothman | 050MX5014B | Done | Y
60 | Text Box | 3 | Adnan Alothman | 050MXXXXX | Equipment were re-tagged according to BAPCO´s instruction (email dated 17 May from Raj Tyagi), final Tag: 050M5098A | N
61 | Text Box | 3 | Adnan Alothman | 050MXXXXX | Equipment were re-tagged according to BAPCO´s instruction (email dated 17 May from Raj Tyagi), final Tag: 050M5098B | N
62 | Text Box | 3 | Adnan Alothman | 050MXXXXX | Equipment were re-tagged according to BAPCO´s instruction (email dated 17 May from Raj Tyagi), final Tag: 050M5099A | N
63 | Text Box | 3 | Adnan Alothman | 050MXXXXX | Equipment were re-tagged according to BAPCO´s instruction (email dated 17 May from Raj Tyagi), final Tag: 050M5099B | N
64 | Text Box | 4 | Adnan Alothman | 050OMG0001 | Done | Y
65 | Text Box | 3 | Adnan Alothman | 7CDU FEED BOOSTER PUMPS MOTOR | Done | Y
66 | Text Box | 3 | Adnan Alothman | 7CDU FEED BOOSTER PUMPS MOTOR | Done | Y
67 | Call-out | 2 | Mahdi Ali | Check sequence number | Sequence number according to unit and documentation issed | Y
68 | Call-out | 1 | Mahdi Ali | Check Sequence number | Sequence number according to unit and documentation issed | Y
69 | Call-out | 3 | MAK | Delete | Done | Y
70 | Call-out | 2 | Mahdi Ali | Delete | Done | Y
71 | Cloud+ | 3 | Adnan Alothman | Equipment To be re-numbered as shown. Note to be added in U010 list. | Done | Y
72 | Cloud+ | 3 | Adnan Alothman | Equipment To be re-numbered as shown. Note to be added in U010 list. | Done | Y
73 | Cloud+ | 3 | Adnan Alothman | Equipment To be re-numbered as shown. Note to be added in U018 list. | Equipment were re-tagged according to instruction from BAPCO (email dated 20 May from Mark Langerhorst) | Y
74 | Cloud+ | 4 | Adnan Alothman | Equipment To be re-numbered as shown. Note to be added in U018 list. | Equipment were re-tagged according to instruction from BAPCO (email dated 20 May from Mark Langerhorst) | Y
75 | Cloud+ | 3 | Adnan Alothman | Equipment To be re-numbered as shown. Note to be added in U019 list. | Done | Y
76 | Cloud+ | 3 | Adnan Alothman | Equipment To be re-numbered as shown. Note to be added in U019 list. | Done | Y
77 | Cloud+ | 4 | Adnan Alothman | Equipment To be re-numbered as shown. Note to be added in U019 list. | Done | Y
78 | Cloud+ | 4 | Adnan Alothman | Equipment To be re-numbered as shown. Note to be added in U019 list. | Done | Y
79 | Cloud+ | 3 | Adnan Alothman | Equipment To be re-numbered as shown. Note to be added in U021 list. | Equipment were re-tagged according to instruction from BAPCO (email dated 20 May from Mark Langerhorst) | Y
80 | Cloud+ | 3 | Adnan Alothman | Equipment To be re-numbered as shown. Note to be added in U021 list. | Equipment were re-tagged according to instruction from BAPCO (email dated 20 May from Mark Langerhorst) | Y
81 | Cloud+ | 3 | Adnan Alothman | Equipment To be re-numbered as shown. Note to be added in U021 list. | Equipment re-numbered according to instruction from BAPCO (email dated 20 May from Mark Langerhorst) | Y
82 | Cloud+ | 4 | Adnan Alothman | Equipment To be re-numbered as shown. Note to be added in U021 list. | Equipment were re-tagged according to instruction from BAPCO (email dated 20 May from Mark Langerhorst) | Y
83 | Text Box | 1 | Yousif Ahmadi | General comments for all Equipment index - Use the new template - Provide Technip Group Spec. 000 GOPS 2014. - Fill the missing cells with the available information. - For new equipment in Existing units use the numbers as were agreed with Bapco. | Answer by each comment: - Update template will be used. - The spec will be send. - The cells filled correpond with the information avalaible. - Done. | Y
84 | Callout | 3 | alexis.martinez | Identified the motor pumps, fans and mixer as M in the driver item means that the driver of the motor is a motor. Review and correct. | Done | Y
85 | Cloud+ | 3 | Adnan Alothman | Motors numbers will be provided later | Equipment were re-tagged according to instruction from BAPCO (email dated 17 May from Raj Tyagi) | Y
86 | Call-out | 4 | Mahdi Ali | New Bapco numbers to be used | Done | Y
87 | Call-out | 3 | MAK | Refer to the Equipment Lists for the existing units and revamp areas that were sent through the Project Mailbox EN0815-PM (Bapco BMP). Follow the equipment numbering given in the lists. | Done, according to instructions from BAPCO | Y
88 | Call-out | 1 | Mahdi Ali | Remove 'f' from the Unit no. | Done | Y
89 | Call-out | 1 | Raj | The Item Index needs to be re-submitted after incorporating Format Changes (Owner had provided comments to TTSJV). Some basis info like equipment tags have been checked in the Item Index as other documents like MSD, PID, Datasheets have not yet been submitted to the Owner | Ok, this comment has been solved because equipment data sheets and MSDs have been issued | Y
90 | Callout | 3 | alexis.martinez | The operating temperature for A/B Crude Oil Tanks on FEED data sheet is 120°F. Review and correct. | Crude operating temperature is between 80ºF and 120ºF. Value shown is aligned with PFD and H&MB balance of upstream/downstream units. | Y
91 | Callout | 3 | alexis.martinez | The pumps motors are not a packages. Why they have Parent Tag Number?. Review and correct. | Parent number is defined as the number associated to a main equipment. eg: The parent number for a pump correspond to its driver (motor/turbine). | N
92 | Call-out | 2 | MAK | This template was revised by Bapco. MOC shall coordinate with JV Directorate for the revised template. | This templeate was revised with JV | Y
93 | Text Box | 1 | MAK | Use the latest document template which is part of the Homogenization Procedure. MOC shall coordinate with JV Directorate. Use A3 landscape document cover page. | Done | Y