## 050-A-PFD-50001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Edgardo | Please indicate the area numbers at all B/L as per BMPS-A-50003. This comment applies to all B/L in this PFD
2 | Typewritten Text | 1 | Nabeel | ADD"#540 R/S"
3 | Typewritten Text | 1 | Nabeel | CHANGE TO "POST"
4 | Typewritten Text | 1 | Nabeel | REMOVE "NNF"
5 | Text Box | 1 | MAK | General Comments applies to all PFDs: 1. Use the latest PFD border and off-page connectors that are part of the Homogenization Procedure. SOC shall coordinate with TTSJV. 2. Total Sheet to be shown as e.g. 023 on all the sheets. 3. Always use NTS for PFD scale. 4. Always use A1 for PFD border size.
6 | Text Box | 1 | MAK | General Comment: Where possible, always align the equipment data block with the respective equipment icon.
7 | Text Box | 1 | MAK | Verify the equipment nos. with the agreed equipment list.
8 | Callout | 1 | Abdul Rahim | if no spill back how C4 injection will be conrtolled
9 | Callout | 1 | Abdul Rahim | add: Banagas fill line to be on tank shell nozzel
10 | Callout | 1 | Abdul Rahim | If naphtha start up is required then check if these pumps require spill back
11 | Call-out | 1 | Edgardo | Please provide stream number (diamond)
12 | Call-out | 1 | Edgardo | insert "pre-BMP".
13 | Call-out | 1 | Edgardo | This Note 14 is more appropriate to be in Sheet 15;If confirm, please delete it from this sheet and transfer it to Sheet 15
14 | Call-out | 1 | Edgardo | This Note 7 seems to be applicable only to Unit 012 and not to Unit 050. Please confirm and if not applicable, please delete this Note
15 | Call-out | 1 | Edgardo | Please insert " STORAGE AND "
16 | Call-out | 1 | Edgardo | This connecting PFD has a newly assigned document number. Please use the newly assigned number
17 | Call-out | 1 | Edgardo | The location of this Note 6 is shown on the B/L and is confusing; Please relocate it somewhere or delete if not necessary. The Note 6 below, however, can be retained
18 | Call-out | 1 | Edgardo | The sheet showing P5027A/B is not included in this PFD. Note that there is a new line connected to pumps mentioned. Please provide the missing sheet
19 | Call-out | 1 | Edgardo | Please provide the stream number (diamond)
20 | Call-out | 1 | Edgardo | Please insert "to R/S "
21 | Call-out | 1 | Edgardo | Please include the words "Gasolene" above the phrase "R/S @2 ......."
22 | Call-out | 1 | Edgardo | Please move the words "LSR / Gasoline " above the phrase "R/S @ 1 ....."
23 | Call-out | 1 | Edgardo | Please indicate the area numbers at the B/L as per BMPS-A-50003. The B/L is between Unit 050 and Unit 930; Hence, the corresponding PFD number of Unit 930 to be shown on the streams to / from Unit 050. This comment applies to all streams B/L in all sheets of Unit 050 PFD which are connected to Unit 930.
24 | Text Box | 1 | Mahdi Ali | The format of this PFD is not acceptable. Follow the latest homogenization procedure.
25 | Text Box | 1 | Mahdi Ali | Use 050-A-PFD-00050-001 for the PFD for the Refinery Tank Farm