## 050-A-PFD-50001-002-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Salman Jaffer | Please revise the data of stream 8 based on addition of the new train in KMU.
2 | Call-out | 1 | 986131 | Add the PFD number of connecting 7CDU
3 | Typewritten Text | 1 | Nabeel | ADD"/NAPHTHA"
4 | Callout | 1 | Abdul Rahim | P1073 is kerosine service
5 | Callout | 1 | Abdul Rahim | as per BOD both 1 HCU and 2 HCU kerosine needs to be directly sent to Sitra Tanks
6 | Call-out | 1 | Edgardo | Please insert "STORAGE AND "
7 | Call-out | 1 | Edgardo | insert "# 540"
8 | Call-out | 1 | Edgardo | Please indicate the unit numbers at the B/L per BMPS-A-50003
9 | Call-out | 1 | Edgardo | Move the the phrase "Sheet 14" inside the offpage connector
10 | Call-out | 1 | Edgardo | The document number of the existing units have been changed. Please use the latest assigned document number issued by Bapco. This comment applies to all document numbers of existing drawings
11 | Call-out | 1 | Edgardo | Please refer to comment in Sheet 1 for comment on B/L between Units 050 and 930