## 050-A-PFD-50001-003-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Abdul Rahim | there should not be a possibility, this needs to be implemented as per BOD
2 | Callout | 1 | Abdul Rahim | show this as solid lines, these will be new lines
3 | Call-out | 1 | Edgardo | insert " STORAGE AND"
4 | Text Box | 1 | Edgardo | Note 7
5 | Text Box | 1 | Edgardo | Note 7
6 | Text Box | 1 | Edgardo | Note 6
7 | Text Box | 1 | Edgardo | 6. 050D0117 / 050D0106 is in 1HCU 10 ppm diesel service pre-BMP 7. 050D0101 / 050D0102 / 050D0111 / 050D0121 are in 2HDU 10 ppm diesel service pre-BMP
8 | Call-out | 1 | Edgardo | insert "BMP"
9 | Call-out | 1 | Edgardo | Please provide stream number (diamond)
10 | Call-out | 1 | Edgardo | Please insert the word "Diesel"
11 | Call-out | 1 | Edgardo | insert "From Manifold"
12 | Call-out | 1 | Edgardo | These equipment are not in this sheet. Please transfer these equipment data in the corresponding sheet where the equipment are shown
13 | Call-out | 1 | Edgardo | Please refer to comment in Sheet 1 for B/L between units 930 and 050