## 050-A-PFD-50001-005-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Abdul Rahim | add a note to check there should be a connection of LSR stream to HRS manifold. this is to route high RVP LSR to HSR tanks
2 | Callout | 1 | Abdul Rahim | change HSR with "Hvy naphtha"
3 | Call-out | 1 | Edgardo | This Note seems to be more applicable to the SGP units instead of unit 050. If confirmed, please delete this note
4 | Call-out | 1 | Edgardo | The sheet number showing these tanks could not be found in this PID. Please note that there is a new line connected to those tanks. Please include the missing sheet
5 | Call-out | 1 | Edgardo | Please refer to comment in Sheet 1 regarding BL between units 930 and 050