## 050-A-PFD-50001-007-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | 986131 | Show LI and Breather valves
2 | Call-out | 1 | 986131 | Show LI and Breather valves
3 | Text Box | 1 | alexis.martinez | General: All Equipment Numbers need to be updated as per the new numbering provided by owner.
4 | Call-out | 1 | alexis.martinez | Add Stream number on the feed of each 1HRCU Feed Tanks.
5 | Call-out | 1 | alexis.martinez | Delete Note 10
6 | Call-out | 1 | alexis.martinez | The legend of new and existing line is not applicable to this PFD because all the lines are new. Delete this legend.
7 | Call-out | 1 | alexis.martinez | The pressure control in both 1RHCU Feed Tanks shall be show both control valves and both pressure control instruments.
8 | Call-out | 1 | alexis.martinez | In the description above the continuation flag, change "7CDU/VDU" to "7VDU/7CDU"
9 | Callout | 1 | Abdul Rahim | indicate set Temperature
10 | Call-out | 1 | Edgardo | Please insert the phrase "and equipment data to be provided and"
11 | Call-out | 1 | Edgardo | Please indicate unit numbers per BMPS-A-50003
12 | Call-out | 1 | Edgardo | These pumps belong to Unit 018 (1RHCU) and will have to be transferred from this PFD to the corresponding PFD of 1RHCU
13 | Call-out | 1 | Edgardo | Please refer to comment in Sheet 1 for B/L between unit 930 and unit 050