## 050-A-PFD-50001-008-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | alexis.martinez | Add stream line number on both A/B Crude Oil Tanks at the Inlet line
2 | Text Box | 1 | alexis.martinez | General: All Equipment Numbers need to be updated as per the new numbering provided by owner.
3 | Typewritten Text | 1 | Nabeel | ADD"D132/D133"
4 | Callout | 1 | Abdul Rahim | delete any reference with decommissioning of existing AB pipelines (this is out BMP scope)
5 | Callout | 1 | Abdul Rahim | existing and new tanks
6 | Callout | 1 | Abdul Rahim | and spare for 1,2 HCU light naphtha /platformate
7 | Callout | 1 | Abdul Rahim | delete
8 | Callout | 1 | Abdul Rahim | add a note: this suction must be done during 4A T&I
9 | Callout | 1 | Abdul Rahim | check if existing lines are adequate
10 | Text Box | 1 | Edgardo | Crude from
11 | Call-out | 1 | Edgardo | insert the word "Crude from"
12 | Text Box | 1 | Edgardo | Slop
13 | Call-out | 1 | Edgardo | insert the word "Slop from "
14 | Text Box | 1 | Edgardo | AB 4
15 | Call-out | 1 | Edgardo | Please provide stream number (diamond)
16 | Call-out | 1 | Edgardo | These pumps belong to Unit 010 and need to be transferred to the corresponding PFD of said unit
17 | Call-out | 1 | Edgardo | replace with AB 1/2/3" Pipelines
18 | Call-out | 1 | Edgardo | Replace with "AB 4"
19 | Text Box | 1 | Edgardo | 14. 050D0139 is in LLCN service pre-BMP
20 | Text Box | 1 | Edgardo | , 14