## 050-A-PFD-50001-009-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Typewritten Text | 1 | Nabeel | WE NEED TO SHOW THE EXISTING CONNECTION OF 14"/C FUEL RETURN FROM SITRA TANKS TO TKS 132/133
2 | Text Box | 1 | 986131 | Add the equipment data blocks for D144 and D124.
3 | Callout | 1 | Abdul Rahim | show also P5033A/B/C discharge to existing A/B tanks
4 | Call-out | 1 | Edgardo | Please provide stream number (diamond)
5 | Text Box | 1 | Edgardo | STORAGE AND
6 | Text Box | 1 | Edgardo | SLOP /
7 | Text Box | 1 | Edgardo | pre-BMP
8 | Call-out | 1 | Edgardo | Please indicate the connecting PFD
9 | Call-out | 1 | Edgardo | Please clarify how the slop from the existing process units can be routed to the slop tanks 050 D0134 and 050D0135
10 | Text Box | 1 | Edgardo | (Non-BMP Units)
11 | Call-out | 1 | Edgardo | insert "Process"
12 | Text Box | 1 | Edgardo | R/S
13 | Call-out | 1 | Edgardo | Please refer to comment in Sheet 1 regarding B/L between units 930 and 050