## 050-A-PFD-50001-010-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | 986131 | note 8 missing, please add.
2 | Typewritten Text | 1 | Nabeel | ADD"D132/D133"
3 | Typewritten Text | 1 | Nabeel | ADD "C-"
4 | Callout | 1 | Abdul Rahim | This PFD has nothing to do with crude except Crude import abd P5033 A/B/C. move this to another PFDDs for better representaion
5 | Call-out | 1 | Edgardo | Please provide stream number (diamod)
6 | Call-out | 1 | Edgardo | Please indicate the unit numbers at the B/L per BMPS-A-50003
7 | Text Box | 1 | Edgardo | STORAGE AND
8 | Text Box | 1 | Edgardo | 8. 050D0142 is in FCCU back-up service pre-BMP
9 | Call-out | 1 | Edgardo | Please provide stream number (diamond)
10 | Call-out | 1 | Edgardo | Please clarify these two lines, which seems to be same; for clarity, please indicate the service name / identification of these existing lines
11 | Call-out | 1 | Edgardo | Same comment as in Sheet 1 regarding B/L between units 930 and 050; also, please use the newly assigned document number of the PFD of existing units