## 050-A-PFD-50001-012-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Abdul Rahim | instead of offspec diesel. change to 3HDU circulation line
2 | Call-out | 1 | Edgardo | Please provide stream number (diamond)
3 | Call-out | 1 | Edgardo | These pumps belong to unit 021. Please transfer these equipment in the corresponding PFD of said unit
4 | Text Box | 1 | Edgardo | 11. 050D1102 is in 2HDU Feed pre-BMP
5 | Text Box | 1 | Edgardo | 12. 050D1201 is in FCCU Feed pre-BMP"
6 | Text Box | 1 | Edgardo | Note 12
7 | Text Box | 1 | Edgardo | Note 11
8 | Call-out | 1 | Edgardo | Refer to comment in Sheet 1 regarding B/L between units 930 and 050