## 050-A-PID-00001-002-R8A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Abdul Rahim | This tie in needs a valve on 4/5 CDU FEED line and to be done during 4A CDU T&I.
2 | Callout | 1 | Abdul Rahim | Slop from units tin in to 10" discharge whereas P5038 min flow is also routed into the same line
3 | Callout | 1 | Abdul Rahim | Needs a valve
4 | Highlight | 1 | Abdul Rahim | . .
5 | Callout | 1 | Abdul Rahim | this is an old suction its integrity to be confirm before use
6 | Callout | 1 | Abdul Rahim | keep all existing un touched because there will be a period all existing and new units are running
7 | Callout | 1 | Abdul Rahim | Indicate P&ID number
8 | Callout | 1 | Abdul Rahim | why RVs are routed to D 134. Should be D164 and D143
9 | Call-out | 1 | Edgardo | Please reverse the arrow head as flow direction is to the tank. See Tie-in 261 below for new flow direction
10 | Call-out | 1 | Edgardo | Please confirm this tie-in during site survey; The new line is 20" while the existing line at location of tie-in is 12"
11 | Text Box | 1 | Edgardo | Please indicate the service name of the tanks; this comment applies to all PIDs where tanks are shown
12 | Call-out | 1 | Edgardo | This Hold item is for the Slop line to 7CDU
13 | Call-out | 1 | Edgardo | Please confirm the requirement for interface point, as the destinations are in the scope of MOC
14 | Callout | 1 | Mahdi Ali | THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINAL HANDOVER AS NEXT REVISION. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
15 | Callout | 1 | Mahdi Ali | BAPCO PROVIDED THIS DRAWING AS REVISION '7'. THUS THIS DRAWING SHALL BE '7A'
16 | Text Box | 1 | Omran A | General Comment Asset no missing?