## 050-A-PID-00002-002-R6A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | A Albalooshi | Please indicate line number
2 | Callout | 1 | A Albalooshi | Please provide the tie-in package for company review and approval. EPC contractor shall note that execution of the tie-ins shall be carried out without jeopardizing the operation and safety of the unit.
3 | Callout | 1 | A Albalooshi | shift the size to the vale
4 | Callout | 1 | Abdul Rahim | As mentioned earlier, tanks T&I are independent of units T&I. But to tie in D139 to 4&5 Feed line 4A needs to be shutdown and 5 CDU to be fed from 5 CDU feed line.
5 | Call-out | 1 | Edgardo | Please confirm the use of pipe spec C3 for this line; this is suction line and source tank has low pressure
6 | Call-out | 1 | Edgardo | Please indicate the stream name "1HCU HSR to HSR Manifold"
7 | Call-out | 1 | Edgardo | This line shall also be hatched, as the source line is already hatched and marked for decommissioning
8 | Call-out | 1 | Edgardo | Please provide this new line with 4" stub with valve and blind to be used during initial filling of tanks
9 | Callout | 1 | Mahdi Ali | BAPCO PROVIDED THIS DRAWING AS REVISION '5'. THUS THIS DRAWING SHALL BE '5A'
10 | Callout | 1 | Mahdi Ali | THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINAL HANDOVER AS NEXT REVISION. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
11 | Typewritten Text | 1 | Nabeel | mention tank service description
12 | Text Box | 1 | Omran A | Enraf Radar Gauge