## 050-A-PID-00004-004-R6A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Abdul Rahim | to be clarified , will there be a valve at unit limit
2 | Callout | 1 | Abdul Rahim | check if P5025 A/B or 5021 A/B. This is to check max inclusion of 1HCU naphtha in a gasoline blend
3 | Callout | 1 | Mahdi Ali | BAPCO PROVIDED THIS DRAWING AS REVISION '5'. THUS THIS DRAWING SHALL BE '5A'
4 | Callout | 1 | Mahdi Ali | THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINAL HANDOVER AS NEXT REVISION. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
5 | Typewritten Text | 1 | Nabeel | Add Spectacle Blind
6 | Typewritten Text | 1 | Nabeel | Should it be sweet MCN or Light Naphtha?
7 | Typewritten Text | 1 | Nabeel | We need to cater for the independent operation of the 1,2 HCU and Sweet MCN