## 050-A-PID-00004-005-R6A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | A Albalooshi | Please provide the tank service
2 | Callout | 1 | Abdul Rahim | Ensure hydraulics are checked, tank minimum operating height to be as existing. if any problem, then suction to be installed on tank bottom
3 | Call-out | 1 | Edgardo | In previous revision of this PID; there is a 1HCU light naphtha line to 50D1401 Platformate R/D; this is now missing in this PID ; Note that this stream is 1HCU light naphtha but the connecting line from 1HCU could not be found
4 | Call-out | 1 | Edgardo | Provide new inlet line with 4" stub with valve and blind for the initial filling of the tanks
5 | Call-out | 1 | Edgardo | Please confirm the requirement for this line; the connecting line is already hatched and decommissioned.
6 | Callout | 1 | Mahdi Ali | THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINAL HANDOVER AS NEXT REVISION. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
7 | Callout | 1 | Mahdi Ali | BAPCO PROVIDED THIS DRAWING AS REVISION '5'. THUS THIS DRAWING SHALL BE '5A'
8 | Typewritten Text | 1 | Nabeel | Change to 1 1/2"