## 050-A-PID-00005-004-R6A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Abdul Rahim | install blind upstream of valve
2 | Callout | 1 | Mahdi Ali | BAPCO PROVIDED THIS DRAWING AS REVISION '5'. THUS THIS DRAWING SHALL BE '5A'
3 | Callout | 1 | Abdul Rahim | need valve
4 | Callout | 1 | Abdul Rahim | Check 16" line adequacy for kero Merox. Note one addiional train was added
5 | Callout | 1 | Francis L | TE insertion length has to be verified for suitability for new line.
6 | Callout | 1 | Abdul Rahim | improve: which kero
7 | Callout | 1 | Abdul Rahim | change to 1 1/2"
8 | Typewritten Text | 1 | Nabeel | to be confirmed!!
9 | Callout | 1 | Abdul Rahim | Provide vent
10 | Call-out | 1 | Edgardo | Please note that if the tank can be shutdown and new permanent inlet nozzles will be installed, the use of inlet diffuser to reduce inlet velocity shall be considered in lieu of the enlarged pipe which require bigger sized valves
11 | Typewritten Text | 1 | Nabeel | Requires high point vent
12 | Callout | 1 | Mahdi Ali | THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINAL HANDOVER AS NEXT REVISION. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
13 | Typewritten Text | 1 | Nabeel | TK Service Description
14 | Callout | 1 | Abdul Rahim | where this valve be installed