## 050-A-PID-00007-001-R6A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Edgardo | Line breaks are long and not easy to identify the connections; please improve the presentation
2 | Call-out | 1 | Edgardo | This line break is long and not easy to identify the connecting lines; please improve presentation
3 | Callout | 1 | Mahdi Ali | BAPCO PROVIDED THIS DRAWING AS REVISION '5'. THUS THIS DRAWING SHALL BE '5A'
4 | Call-out | 1 | Edgardo | The location of this tie-in needs to be confirmed through hydraulic studies also, Owner's concern is the potential negative impact to the feed to 2HDU, which is gravity fed
5 | Call-out | 1 | Edgardo | Please clarify the scope of Tie-in 263; this seems to be for a new line (Line number P1258); however, there is no tie-in shown on existing line P2442
6 | Callout | 1 | Mahdi Ali | THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINAL HANDOVER AS NEXT REVISION. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
7 | Call-out | 1 | Edgardo | Please complete the information for the off-page connector