## 050-A-PID-00008-005-R5A-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Typewritten Text | 1 | Nabeel | Define the stream????
2 | Callout | 1 | Francis L | This unit has conventional analog system. Hence, use conventional analog system, but not FF..
3 | Callout | 1 | Mahdi Ali | THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINALHANDOVER. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
4 | Callout | 1 | Abdul Rahim | Pls check for check valves requirement of P1014/1021/1022. to prevent reverse flow
5 | Text Box | 1 | Mahdi Ali | THIS DRAWING WAS PROVIDED AS REV '4'; THUS THIS DRAWING SHALL BE REV '4A'
6 | Typewritten Text | 1 | Nabeel | What are these streams? Add description
7 | Call-out | 1 | Ali Abbas | confirm/show correct signal type. General comments