## 050-A-PID-00009-001-R6A-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mahdi Ali | THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINALHANDOVER. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
2 | Text Box | 1 | Mahdi Ali | THIS DRAWING WAS PROVIDED AS REV '5'; THUS THIS DRAWING SHALL BE REV '5A'
3 | Callout | 1 | Abdul Rahim | May be the location of this tie in is not correct. alternative is to be taken from West Manifold,, to be confirmed during site survey. tie in to be done during 4A and 5 CDU T&I if no isolation is available in Tank farm
4 | Call-out | 1 | Edgardo | Please clarify the requirement for interface point at this line, as the destination equipment is in scope of MOC