## 050-A-PID-00010-001-R6A-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Abdul Rahim | confirm if 8" is adequate for max slopping
2 | Typewritten Text | 1 | Nabeel | this is not a floating roof its open tank
3 | Callout | 1 | Abdul Rahim | needs valves and blind
4 | Callout | 1 | Abdul Rahim | delete, all slops unleaded
5 | Callout | 1 | Mahdi Ali | THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINALHANDOVER. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
6 | Callout | 1 | Abdul Rahim | where will be the location of this valve
7 | Callout | 1 | Abdul Rahim | change to Crude line R/V
8 | Callout | 1 | Abdul Rahim | install this valve here
9 | Text Box | 1 | Mahdi Ali | THIS DRAWING WAS PROVIDED AS REV '5'; THUS THIS DRAWING SHALL BE REV '5A'
10 | Text Box | 1 | Edgardo | Please clarify how the slop from existing process units can be routed to the new slop tanks 050D135 and 050D134
11 | Callout | 1 | Abdul Rahim | need to see P&ID arrangement of each unit discharing into this 14" common line
12 | Callout | 1 | Abdul Rahim | indicate line size
13 | Callout | 1 | Abdul Rahim | need to show AB4 R/V discharge to Tank 164 and its spare tank 143
14 | Callout | 1 | Abdul Rahim | pls check if 12" is adequate for max slopping