## 050-A-PID-00012-001-R5A-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Abdul Rahim | check adequacy of P5025 A/B, if not adequate use P5021 A/B
2 | Callout | 1 | Mahdi Ali | THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINALHANDOVER. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
3 | Text Box | 1 | Mahdi Ali | THIS DRAWING WAS PROVIDED AS REV '4'; THUS THIS DRAWING SHALL BE REV '4A'
4 | Callout | 1 | Abdul Rahim | this tie in may be not correct. if P5025 are used for 1/2 HCU light naphtha then tanks 108 and 1108 suction needs to be tied in in to P5025. pls discuss
5 | Callout | 1 | Mahdi Ali | REMOVE THE LINE BREAK