## 050-A-PID-50001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Francis L | Consider indicating a key switch (XHS) for each pump on P&ID.
2 | Text Box | 1 | Abdul Majeed | electric line
3 | Call-out | 1 | MAK | General Comment to be applied to all P&IDs: As per BMPS-A8, Section 8.4.3, Drivers Tag Nos. e.g. Motors/Turbines shall always be inserted in all P&IDs and placed below the parent equipment no. e.g. Pump/Fan/Mixer/Cooler where possible. Motor FinFan tag nos. shall always be shown where applicable.
4 | Callout | 1 | Francis L | Indicate tag no.
5 | Text Box | 1 | MAK | General Comment: Refer to BMPS-J3 for the correct tagging of Relief Valves.
6 | Cloud+ | 1 | MAK | Delete on all sheets
7 | Call-out | 1 | Edgardo | Please use the new drawing number, if available; please confirm also if the interface point is at this line, as the destination is with the scope of MOC
8 | Typewritten Text | 1 | Nabeel | Change to 050D0152
9 | Callout | 1 | Francis L | Add a local FI on loop and associate with relevant valve. Applies to all other similar loops.
10 | Text Box | 1 | MAK | 050M5080C
11 | Callout | 1 | Abdul Rahim | Why Pump number is same as motor number
12 | Callout | 1 | Francis L | Confirm the need for diaphragm seals.
13 | Call-out | 1 | Edgardo | Please clarify if there is requirement to control flow to 7CDU and how this is done; no control valve is shown in 050 PID
14 | Callout | 1 | Abdul Rahim | Rewrite: Crude oil if required is sent to storage tanks at Sitra Tanks used in crude service D741 or D760
15 | Text Box | 1 | Mahdi Ali | THIS APPLICABLE FOR ALL THE PIDS. 1. TAG NUMBER FOR THE DRIVER FOR ROTATING EQUIPMENT SUCH AS PUMPS OR COMPRESSORS SHALL BE INSERTED ON ALL PIDS AS PER BMPS-A8 SECTION 8.4.3 2. USE UPDATE LINE TYPE FOR FIELDBUS SIGNAL 3. SEQUENCE NUMBER FOR EQUIPMENT SHALL HAVE 4 DIGITS. REFER TO NOTES AND OPCs
16 | Text Box | 1 | MAK | 050M5080A
17 | Text Box | 1 | MAK | 050M5080B
18 | Callout | 1 | Abdul Rahim | why Motor number is not same as pump number
19 | Callout | 1 | Francis L | Show as a dashed signal. Applies to all other similar and relevant signals.
20 | Callout | 1 | Mahdi Ali | EQUIPMENT TAGS NOT AS PER THE BMPS-A8