## 050-A-PID-50002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Francis L | Provide a local FI with readability from required valve (indicate tag no.)
2 | Callout | 1 | Abdul Rahim | Motor number is show on the previuos page why not here
3 | Typewritten Text | 1 | Nabeel | Add 050D0138
4 | Callout | 1 | Abdul Rahim | the pump
5 | Callout | 1 | Abdul Rahim | will be discussed during P&ID review meeting
6 | Call-out | 1 | Edgardo | Please clarify if there is requirement to control injection rate to 7CDU, as no control valve is shown in this PID
7 | Callout | 1 | Francis L | Is a local FI required?