## 050-A-PID-50009-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Edgardo | Please confirm line number; this is shown as Line P1351 in 050-A-PID-00006-001
2 | Typewritten Text | 1 | Nabeel | /050P1073/050P0957
3 | Callout | 1 | Francis L | Should be an instrument tag.
4 | Callout | 1 | Abdul Rahim | Pls confirm if ! and 2 HCU will be routed to Sitra Tanks directley
5 | Typewritten Text | 1 | Nabeel | Replace with 1 1/2"
6 | Text Box | 1 | Abdul Rahim | Is this P&ID necessary.
7 | Call-out | 1 | Edgardo | Please clarify if these valves should be normally blinded, to ensure positive isolation.
8 | Callout | 1 | Abdul Rahim | Improve the title