## 050-A-PID-55001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Abdul Rahim | # 7 CDU | It has been agreed to keep it as it is. | N
2 | Text Box | 1 | Mahdi Ali | 050-A-PID-00001-01 | It will be updated to corresponding P&ID in next issue. | Y
3 | Call-out | 1 | Ahmed Marhoon | Add a note to describe the SEQ. | It will be included the sequence for MOVs description | Y
4 | Callout | 1 | Abdul Rahim | also add capacity at max height | it will be included as a note | Y
5 | Typewritten Text | 1 | Nabeel | Change to "050MX0013A/B" | To be updated according to latest Equipment List. | Y
6 | Callout | 1 | Abdul Rahim | confirm the spill back is routed to the suction or as per this PID into the tank. | Pump min. Flow line connects to the tank as shown. | N
7 | Callout | 1 | Abdul Rahim | confirm this #7 CDU booster is P5032A/B | To be confirmed with final resolution of tank unit and booster pump area designation | N
8 | Callout | 1 | Abdul Rahim | detailed drawing is required for tank internal and external components | Internals will be shown accordingly. | Y
9 | Callout | 1 | alexis.martinez | Each propeller mixer shall be shown separated and the the associated instrumentation as well. | It will be included in next issue | Y
10 | Callout | 1 | Robert.Kawitzki | Equipment numbering as per BMPS A8 7.2.5.4 | It will be numbered according to Equipment list | Y
11 | Typewritten Text | 1 | Nabeel | Follow Bapco numbering change to "050MX0013A/B" | It will be numbered according to Equipment list | Y
12 | Callout | 1 | Abdul Rahim | for crude tanks two independant stilling well is required one for radar gauge and one for manual gauging. Ask for standard drawing from owner. | Noted. | Y
13 | Callout | 1 | alexis.martinez | For level on continuation flags "12469" and "3800" replace "010P031A/B" by "010P0031A/B" | It will be updated with final tagging of pump area. | Y
14 | Call-out | 1 | Ali Abbas | For overfill protection, MOV to be linked to LSH to close MOV. To be further discussed during Hazop. This is a general comments for all the Tanks. | It will be included through dcs if is required during hazop | N
15 | Call-out | 1 | Ali Abbas | For still well size and arrangements to follow Owner standard drawing including Thermowell installation. This is a general comments for all the Tanks. | Noted. For multipoint TE involved in TGS, stilling well may be different according to TGS Vendor recommendations. Some Vendors use a holed stilling well (when the tank is not pressurized) in order to measure the water at the bottom (fluid has to be in contact with the sensor). To be discussed in a further stage. | Y
16 | Callout | 1 | Abdul Rahim | for temperature normally is not holed stilling well. pls confirm | It will be confirmed according to Std dwg. | Y
17 | Call-out | 1 | A.Jabbar Mahmood | Further clarify note 3 (what is meant by Working Volume?) | Note 3 will be modified in order to include clarification of working volume meaning (Volume between HLL and LLL) | Y
18 | Text Box | 1 | Mahdi Ali | General Comments 1. Use latest border that is part of the Homogenization procedure. 2. Scale of the drawing to be: NTS 3. Total Sheets to be in 3 digits, i.e 001 4. All equipment tags to have unit number as a prefix. This includes the tag numbers above the Off-page connectors. 5. All text heights to be same for General Notes and Notes. | This will be included in next issue accordingly | Y
19 | Call-out | 1 | Ahmed Marhoon | General for LA: add a note describing the common alarm for low low and high high level | It will be included a note next to LA | Y
20 | Callout | 1 | alexis.martinez | GENERAL: As per BMPS-A8, the streams leaving or enter the P&ID shall Include the name of the equipment and the complete tag number. Also the unit number abbreviated name when it is from/to other unit. | Noted. | Y
21 | Call-out | 1 | Ali Abbas | GWR suitability for this application to be confirmed. This is a general comments for all the Tanks. | It will be changed to RADAR. Nevertheless, final instrument to be used for this application is being studied, and it will be defined in a later stage. | N
22 | Callout | 1 | Abdul Rahim | indicate tank number | It has been agreed to keep it as it is. | N
23 | Callout | 1 | Abdul Rahim | indicate what of valve | It will be confirmed according to JVD instruction for this particular service | N
24 | Callout | 1 | Abdul Rahim | is there any diffuser in side the tank | It will be shown the deep pipe in the P&ID | Y
25 | Callout | 1 | Abdul Rahim | is this suction line tank bottom nozzle or shell nozzle | Connection is in shell as shown. | N
26 | Call-out | 1 | Ali Abbas | Lcal panel requirement to be discussed | It will be finalized once received information from JVD, regarding the optimization of the panels. | N
27 | Call-out | 1 | Ali Abbas | Link associated LI to the SEQ logic for Mixer stop on low level. General comments for all Tanks. | Seq link will be included to stop mixers in Low Low Liquid Level, note 14 will be deleted to avoid duplicity of information. | Y
28 | Call-out | 1 | Ali Abbas | Note 4 is not referenced near the TW. General comments for all Tanks. | Note 6 presence on P&ID is related to comment 15. Stilling well for TE involved in TGS should be holed. Therefore, otherwise decided by Owner, note 6 remains next to TE on the top of the tanks. | Y
29 | Typewritten Text | 1 | Nabeel | Note 7 | Noted. | Y
30 | Call-out | 1 | Edgardo | Please change drain size to 1 1/2" to facilitate ease of draining line during maintenance work; The line is long and its volume of content, if required to be drained, is significant | Drain size will be increased to 1-1/2". | Y
31 | Call-out | 1 | Edgardo | please confirm the appropriate location of the suction nozzle - either at shell or at bottom | Refer to comment ID 25 | N/A
32 | Call-out | 1 | 986131 | Please review the sample type as 15 is for normal product. This is a high viscosity service and also a at high temperature which would need cooling before sample is collected. | This crude is at 80F, it is not a high temperature service, According to BMPS-A-50003 type 15 is correct. | N
33 | Call-out | 1 | Ahmed Marhoon | Review requirements for low and high level alarm for operator action. To be confirmed during Hazop3 | It will be checked if required, for operator action. | N
34 | Call-out | 1 | 986131 | Review the need for steam tracing the line. | According to 010-A-BOD-00001-001 paragraph 15. Crude pour point is between -36 to -15 ºC at amb conditions, therefore it is not required a steam trace for SP lines. | N
35 | Call-out | 1 | 986131 | Review the requirement to steam trace the valve and the line up to the tank. | it will be revised in accordance to comment ID 34 | N
36 | Callout | 1 | Abdul Rahim | rewrite in full | According to BMPS-A8 full description of the unit is shown in Unit: field. For commented field is required short description. | N
37 | Callout | 1 | Abdul Rahim | rim vent requirment to be approved by owner | The vent is required as per BAPCO request. | N/A
38 | Callout | 1 | Abdul Rahim | sheet number are not clear can not be followed | It will be confirmed according to JVD instruction. | Y
39 | Call-out | 1 | Edgardo | Show the B/L;this line is connected to Unit 010 | To be confirmed with final resolution of tank unit and booster pump area designation | N
40 | Call-out | 1 | Abdulaziz | Tank mixer shall be provided with clear maintenance access for removal and installation | Accesibility is accounted for and it will be included in 3D Model. | N
41 | Callout | 1 | Robert.Kawitzki | Text size to be as per BMPS A8 | Text is according to SPPID database, it will be confirmed if any additional requirement is to be modified. | N/A
42 | Text Box | 1 | Mahdi Ali | This is existing Unit and TTSJV shall obtain the drawing number from Bapco. The Crude FEED and Rundown System carry 050-A-PID-00001 sequence number and this drawing shall be continuation to the existing PIDs but sheets to be added. | Document numbering was assigned by JVD, Bapco to confirm this numbering | N/A
43 | Callout | 1 | Abdul Rahim | this should read working capacity i.e capacity at max height - capacity at min height | it will be included as a note. | Y
44 | Callout | 1 | Robert.Kawitzki | Title block to be complete | It will remain as shown. | N/A
45 | Call-out | 1 | A.Jabbar Mahmood | Typical comment: Show the drawing numbers of all incoming and outgoing streams | It will be included in next issue. | Y
46 | Call-out | 1 | Ahmed Marhoon | Unlike the MOV at the tank's outlet, different serial numbers are assigned for the MOV-1001 and its accessories. Standardize wherever possible. Contractor to clarify. | Limit switches have been renamed. In paralel, it will be confirmed with ROC if it is possible to rename limit switches tags according to MOV tag number. | Y
47 | Typewritten Text | 1 | Nabeel | We should have a Thermal Relief valve on the line between to valves | It is not required due to operating philosophy of this tank. | N
48 | Typewritten Text | 1 | Nabeel | What is "LLL"? | To be included in letters Low Low Liquid Level | Y