## 050-A-PID-55001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Abdul Rahim | # 7 CDU
2 | Text Box | 1 | Mahdi Ali | 050-A-PID-00001-01
3 | Call-out | 1 | Ahmed Marhoon | Add a note to describe the SEQ.
4 | Callout | 1 | Abdul Rahim | also add capacity at max height
5 | Typewritten Text | 1 | Nabeel | Change to "050MX0013A/B"
6 | Callout | 1 | Abdul Rahim | confirm the spill back is routed to the suction or as per this PID into the tank.
7 | Callout | 1 | Abdul Rahim | confirm this #7 CDU booster is P5032A/B
8 | Callout | 1 | Abdul Rahim | detailed drawing is required for tank internal and external components
9 | Callout | 1 | alexis.martinez | Each propeller mixer shall be shown separated and the the associated instrumentation as well.
10 | Callout | 1 | Robert.Kawitzki | Equipment numbering as per BMPS A8 7.2.5.4
11 | Typewritten Text | 1 | Nabeel | Follow Bapco numbering change to "050MX0013A/B"
12 | Callout | 1 | Abdul Rahim | for crude tanks two independant stilling well is required one for radar gauge and one for manual gauging. Ask for standard drawing from owner.
13 | Callout | 1 | alexis.martinez | For level on continuation flags "12469" and "3800" replace "010P031A/B" by "010P0031A/B"
14 | Call-out | 1 | Ali Abbas | For overfill protection, MOV to be linked to LSH to close MOV. To be further discussed during Hazop. This is a general comments for all the Tanks.
15 | Call-out | 1 | Ali Abbas | For still well size and arrangements to follow Owner standard drawing including Thermowell installation. This is a general comments for all the Tanks.
16 | Callout | 1 | Abdul Rahim | for temperature normally is not holed stilling well. pls confirm
17 | Call-out | 1 | A.Jabbar Mahmood | Further clarify note 3 (what is meant by Working Volume?)
18 | Text Box | 1 | Mahdi Ali | General Comments 1. Use latest border that is part of the Homogenization procedure. 2. Scale of the drawing to be: NTS 3. Total Sheets to be in 3 digits, i.e 001 4. All equipment tags to have unit number as a prefix. This includes the tag numbers above the Off-page connectors. 5. All text heights to be same for General Notes and Notes.
19 | Call-out | 1 | Ahmed Marhoon | General for LA: add a note describing the common alarm for low low and high high level
20 | Callout | 1 | alexis.martinez | GENERAL: As per BMPS-A8, the streams leaving or enter the P&ID shall Include the name of the equipment and the complete tag number. Also the unit number abbreviated name when it is from/to other unit.
21 | Call-out | 1 | Ali Abbas | GWR suitability for this application to be confirmed. This is a general comments for all the Tanks.
22 | Callout | 1 | Abdul Rahim | indicate tank number
23 | Callout | 1 | Abdul Rahim | indicate what of valve
24 | Callout | 1 | Abdul Rahim | is there any diffuser in side the tank
25 | Callout | 1 | Abdul Rahim | is this suction line tank bottom nozzle or shell nozzle
26 | Call-out | 1 | Ali Abbas | Lcal panel requirement to be discussed
27 | Call-out | 1 | Ali Abbas | Link associated LI to the SEQ logic for Mixer stop on low level. General comments for all Tanks.
28 | Call-out | 1 | Ali Abbas | Note 4 is not referenced near the TW. General comments for all Tanks.
29 | Typewritten Text | 1 | Nabeel | Note 7
30 | Call-out | 1 | Edgardo | Please change drain size to 1 1/2" to facilitate ease of draining line during maintenance work; The line is long and its volume of content, if required to be drained, is significant
31 | Call-out | 1 | Edgardo | please confirm the appropriate location of the suction nozzle - either at shell or at bottom
32 | Call-out | 1 | 986131 | Please review the sample type as 15 is for normal product. This is a high viscosity service and also a at high temperature which would need cooling before sample is collected.
33 | Call-out | 1 | Ahmed Marhoon | Review requirements for low and high level alarm for operator action. To be confirmed during Hazop3
34 | Call-out | 1 | 986131 | Review the need for steam tracing the line.
35 | Call-out | 1 | 986131 | Review the requirement to steam trace the valve and the line up to the tank.
36 | Callout | 1 | Abdul Rahim | rewrite in full
37 | Callout | 1 | Abdul Rahim | rim vent requirment to be approved by owner
38 | Callout | 1 | Abdul Rahim | sheet number are not clear can not be followed
39 | Call-out | 1 | Edgardo | Show the B/L;this line is connected to Unit 010
40 | Call-out | 1 | Abdulaziz | Tank mixer shall be provided with clear maintenance access for removal and installation
41 | Callout | 1 | Robert.Kawitzki | Text size to be as per BMPS A8
42 | Text Box | 1 | Mahdi Ali | This is existing Unit and TTSJV shall obtain the drawing number from Bapco. The Crude FEED and Rundown System carry 050-A-PID-00001 sequence number and this drawing shall be continuation to the existing PIDs but sheets to be added.
43 | Callout | 1 | Abdul Rahim | this should read working capacity i.e capacity at max height - capacity at min height
44 | Callout | 1 | Robert.Kawitzki | Title block to be complete
45 | Call-out | 1 | A.Jabbar Mahmood | Typical comment: Show the drawing numbers of all incoming and outgoing streams
46 | Call-out | 1 | Ahmed Marhoon | Unlike the MOV at the tank's outlet, different serial numbers are assigned for the MOV-1001 and its accessories. Standardize wherever possible. Contractor to clarify.
47 | Typewritten Text | 1 | Nabeel | We should have a Thermal Relief valve on the line between to valves
48 | Typewritten Text | 1 | Nabeel | What is "LLL"?