## 050-A-PID-55006-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Ali Abbas | Add a note stating that all instrumentation connected to the PIT shall be accessible readable and accessible from outside the pit. | To be check for standarization through all the units | Y
2 | Text Box | 1 | Ahmed Ali | please refer to the general item raised by owner regarding Pits. "provide grating to cover the pit also provide safety barricate and ladder as appropiated and dewatering arrangement. | A note will be included to follow the spec according to BMPS-A50003 | Y
3 | Callout | 1 | Abdul Rahim | this has nothing to do with Refinery Tank unit 050. change title | This P&ID will be reissued once confirmed the final numbering for booster pump area. | Y
4 | Text Box | 1 | alexis.martinez | This P&ID is not related with 1RHCU Feed Tanks or A/B Crude Oil Tanks. | This P&ID will be reissued once confirmed the final numbering for booster pump area. | Y