## 050-A-PID-55011-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | Delete
2 | Callout | 1 | alexis.martinez | GENERAL: The description on continuation flag shall be as per BMPS-A8.
3 | Call-out | 1 | Edgardo | Please clarify the Unit Number; noted in the Offpage connector that the stream is from Unit 934 PID
4 | Call-out | 1 | Sameer Foujdar | Flushing oil supply to be described completely where it is routed.
5 | Call-out | 1 | Sameer Foujdar | Flushing oil supply to be described completely where it is routed.
6 | Callout | 1 | Berik.Nurbolatov | STATIC
7 | Call-out | 1 | Edgardo | The valves, instruments, blinds at the Unit 50 / 930 B/L are not required; However, please ensure that the required isolation valves, instruments, blinds are provided at the B/L of the respective process units where these streams are connected
8 | Call-out | 1 | Sameer Foujdar | Ensure the description is matching the description given in PID for unit 930 sheet no 2.
9 | Call-out | 1 | Sameer Foujdar | The line numbers are different for the same line in PID for unit 930 sheet no 2.
10 | Callout | 1 | alexis.martinez | The instrumentation arrangement for "Blend Crude Oil to 7CDU" and "Vacuum Residue to 1RHCU" are not consistent. Review
11 | Text Box | 1 | Sameer Foujdar | General Comment: All the connecting nodes cannot be traced on the PID for unit 930. Unit 930 PID to be updated to reflect the connecting nodes.
12 | Text Box | 1 | alexis.martinez | GENERAL:The line and continuation flag shall have the same Unit number