## 050-A-PID-55011-002-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Edgardo | Comment shown in 050-A-PID-55011-001 regarding the B/L valves also apply to this sheet
2 | Cloud+ | 1 | MAK | Delete
3 | Text Box | 1 | alexis.martinez | This is an Interconnecting P&ID. All the lines are not part of 7CDU, 1RHCU, 2HCU or 3HDU feed tanks or pumps. Should be deleted
4 | Call-out | 1 | Sameer Foujdar | Review the Start-up Naphtha line to 7CDU/7VDU as it is not shown on PID for unit 930 sheet no 1.
5 | Text Box | 1 | Edgardo | The above lines are already reflected in the respective Unit 050 PID shown in the Offpage connector, except the interface point; These lines can be deleted from this sheet and the relevant interface point to be transferred to the relevant PID;
6 | Callout | 1 | alexis.martinez | GENERAL: Review the connector numbers in continuation flag. it could not be found in unit 930.
7 | Call-out | 1 | Sameer Foujdar | Correct the spelling to NAPHTHA
8 | Call-out | 1 | Sameer Foujdar | Change the description to HSR from 7CDU/SGP
9 | Call-out | 1 | Sameer Foujdar | Correct the spelling to NAPHTHA