## 050-A-PID-55011-004-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Sameer Foujdar | Change the description to SR Diesel/LVGO from 7CDU
2 | Call-out | 1 | Hasan Al Noaimi | Delete. diesel from this unit is 10ppm
3 | Cloud+ | 1 | MAK | Delete
4 | Text Box | 1 | alexis.martinez | This is an Interconnecting P&ID. All the lines are not part of 7CDU, 1RHCU, 2HCU or 3HDU feed tanks or pumps. Should be deleted
5 | Call-out | 1 | Sameer Foujdar | Check and confirm the line size is 6" as per PID for unit 930 sheet no 2.
6 | Call-out | 1 | Ahmed Ali | Review type of valves
7 | Call-out | 1 | Sameer Foujdar | Change the description to SR MVGO/HVGO from 7CDU
8 | Text Box | 1 | Edgardo | These lines are already reflected in the respective Unit 050 PID shown in the Offpage connector, except the interface point; these lines can be deleted from this sheet and the relevant interface point transferred to the respective Unit 050 PID
9 | Call-out | 1 | Sameer Foujdar | Change the description to COLD MVGO from 1RHCU
10 | Call-out | 1 | Edgardo | Comment shown in 050-A-PID-55011-001 regarding the B/L valves also apply to this sheet
11 | Call-out | 1 | Hasan Al Noaimi | 3HDU