## 050-A-STS-50001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mahdi Ali | THIS DOCUMENT IS A CALCULATION SHEET AND NOT A STUDY. THUS THE DOCUMENT TYPE SHALL BE 'CAL' AND NOT 'STS'. CHANGE ALL THE REFERENCES TO THIS DOCUMENT ACCORDIGNLY. HOWEVER, IF THIS DOCUMENT IS A STUDY THEN THE TITLE SHOULD BE CHANGED ACCORDINGLY.
2 | Text Box | 1 | MAK | Bapco has not received the Unit Equipment List (Item Index) for review. How to cross check the correctness/completeness of equipment numbers within this document?? Equipment List is the master index and shall be issued before issuing this document.
3 | Text Box | 2 | Abdul Rahim | same as above
4 | Text Box | 2 | A Albalooshi | Please define the criticality rating codes i.e. A,B,C,D as a note below. Also please define the numbers of severity etc..
5 | Typewritten Text | 2 | steven.coyne | Reference: Criticality PROCEDURE 000-A-PRO-50017-001
6 | Text Box | 2 | A Albalooshi | Please relate the criticality ratings with the inspection levels.
7 | Text Box | 2 | MAK | General Comment: Equipment List for Unit 050 was not issued for review. However, this list shall perfectly match Unit 050 - Equipment List (Item Index). All Units equipment shall be included for Criticality Rating Evaluation.