## 050-A-STS-55001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | General Comment: For all documents, use the latest document template that is part of the Homogenisation Procedure.
2 | Text Box | 1 | MAK | General Comment: The equipment nos. in this document shall perfectly match the Equipment List (Item Index). Add the missing equipment.
3 | Callout | 1 | Mahdi Ali | INCORRECT DOCUMENT TYPE FOR CALCULATION SHEET. USE 'CAL'
4 | Cloud+ | 1 | Mohamed Ayyash | Project number missing
5 | Cloud+ | 1 | Mohamed Ayyash | Unit name/number missing
6 | Text Box | 2 | giovanny.rodriguez | EQUIPMENT LIST FOR UNIT 050 INCLUDES 46 TAGS (INCLUDING EQP TAGS WITHIN OTHER OTHER UNITS), ALL UNITS EQUIPMENT SHALL BE INCLUDED FOR CRITICALITY RATING EVALUATION
7 | Text Box | 2 | alexis.martinez | Include in the document the notes, reference and the meaning of all the abbreviations for clarity of the document.
8 | Text Box | 2 | Abdulaziz | Mixer motors shall be revised and included in the list
9 | Callout | 2 | Fernando.Perez | Motors to be included in Critically Rating