## 050-D-DAT-55001-001-R0
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Stamp | 1 | Adnan Alothman
2 | Text Box | 1 | Ahmed.Marhoon | Comments on Instrumentation and Control scope have not been closed appropriately. Several comments have been captured on the GAD of this equipment and the closure notes/replies were not accepted by Owner. Contractor is fully responsible to adequately address the comments provided on the GAD and ensure consistency between documents post resolution of these comments.
3 | Text Box | 2 | giovanny.rodriguez | PLEASE USE COMMERTIAL THK OR mm, (COMMERTIAL THK. ARE UP TO BASE /16)
4 | Callout | 2 | Abdul Rahim | Confirm this temperature
5 | Callout | 2 | Abdul Rahim | require full access wind grider
6 | Callout | 2 | Abdul Rahim | confirm the SG
7 | Callout | 3 | giovanny.rodriguez | BMPS-D4
8 | Text Box | 3 | giovanny.rodriguez | BMPS-D1 & BMPS-D2
9 | Text Box | 3 | giovanny.rodriguez | CONTRACTOR
10 | Text Box | 3 | giovanny.rodriguez | SEE BMPS-D2 ANNEX C
11 | Callout | 3 | giovanny.rodriguez | BMPS-D4
12 | Text Box | 3 | giovanny.rodriguez | BMPS-B9
13 | Text Box | 3 | giovanny.rodriguez | CONTRACTOR
14 | Callout | 4 | Abdul Rahim | if this means tank measurement from control room then "yes"
15 | Text Box | 5 | giovanny.rodriguez | BMPS-D2 ANNEX C3.11 36"
16 | Callout | 10 | Abdul Rahim | is 3" sufficient clearance
17 | Callout | 10 | Abdul Rahim | this should be design max AB4 crude line rate 400 MBPD
18 | Call-out | 10 | Ahmed.Marhoon | Contractor to ensure compliance to the latest standard drawing.
19 | Callout | 10 | Abdul Rahim | do not used taper type sewer box
20 | Text Box | 11 | giovanny.rodriguez | B7 - UPDATE ACCORDINGLY
21 | Callout | 11 | Abdul Rahim | final color to be same as existing tanks color at Refinery and Sitra Tanks
22 | Callout | 11 | giovanny.rodriguez | IDEM TO 5)
23 | Callout | 11 | giovanny.rodriguez | YES BMPS-B7, REFER TO BMPS-D2 ANNEX C.4.7
24 | Text Box | 11 | giovanny.rodriguez | NOT PAINTED??