## 050-D-DAT-55003-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | General Comment: Use the latest cover sheet which is part of the Homogenization Procedure. TR shall coordinate with JV Directorate.
2 | Text Box | 1 | alexis.martinez | General: All Equipment Number need to be updated as per the new numbering provided by owner
3 | Text Box | 1 | Ahmed Marhoon | Refer to comments provided on 050-D-GAD-55003 sheets and ensure consistency between documents post implementation of the comments.
4 | Cloud+ | 2 | Mohamed Ayyash | Delete "f"
5 | Call-out | 2 | Edgardo | for clarity, please modify format of text. As example, this can be shown as 96" W x 55/64" thick
6 | Call-out | 2 | Edgardo | Please clarify this requirement. Tank will be cone roof type and typically there is no wind girder unless required as per design
7 | Callout | 3 | Erwin.Lugue | All load units shall be in S.I.
8 | Callout | 4 | Erwin.Lugue | All load units shall be in S.I.
9 | Cloud+ | 5 | Mohamed Ayyash | Move to center of cell
10 | Callout | 5 | alexis.martinez | Page 5. Include as per P&ID 050-A-PID-55003-001 and General arrangement 050-D-GAD-55003 (4 sheets), the number of nozzles and size.
11 | Call-out | 5 | Edgardo | Please change "Hot" to "Heat"
12 | Call-out | 5 | Edgardo | Please reconfirm the nozzle size for the nitrogen blanketing
13 | Cloud+ | 5 | Mohamed Ayyash | Write "Datum" on one line. Adjust font or column width
14 | Cloud+ | 5 | Mohamed Ayyash | Write "Dimension" and "Finish" on one line. Adjust font or column width
15 | Cloud+ | 5 | Mohamed Ayyash | Write "schedule" on one line. Adjust font or column width
16 | Cloud+ | 6 | Mohamed Ayyash | Move to center of cell
17 | Callout | 6 | alexis.martinez | Pages 5 and 6. Move the sections 24,25,26,27 and 28 after section 23. Avoid split table 3 to insert section in between.
18 | Cloud+ | 6 | Mohamed Ayyash | Write "Datum" on one line. Adjust font or column width
19 | Cloud+ | 6 | Mohamed Ayyash | Write "Dimension" and "Finish" on one line. Adjust font or column width
20 | Cloud+ | 6 | Mohamed Ayyash | Write "schedule" on one line. Adjust font or column width
21 | Call-out | 10 | Abdulaziz | Minimum clearances of 3" shall be provided between the roof minimum level and the mixer component at low level as per API 650
22 | Call-out | 10 | Edgardo | Please change "hot" to "Heat"
23 | Call-out | 12 | Jawad Alawi | Paint system should consider CUI and latest NACE SP0198 recommendations.