## 050-D-DAT-55003-001-RB
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | Mohamed Ayyash | Should read 1/12. Why delete the page number on the cover page? Need to be consistent with BMP documents of which all consider the cover page as page one.
2 | Cloud+ | 1 | Mohamed Ayyash | Unit name/no. missing
3 | Text Box | 1 | Ahmed.Marhoon | JV replies on comments related to instrumentation and control scope in previous revision need to be discussed with the concerned personnel at the MOC for mutual agreement on way forward.
4 | Cloud+ | 1 | Mohamed Ayyash | Project No. missing
5 | Callout | 2 | Erwin.Lugue | Refer to BPMS-A1 sec 10.7.1
6 | Callout | 5 | alexis.martinez | Page 5. The size of Nozzle 15N is 8" in General Arrangement document 050-D-GAD-55003-001. Review and correct accordingly.
7 | Callout | 5 | alexis.martinez | Page 5. The size of Nozzle 7CN is 4" in General Arrangement document 050-D-GAD-55001-001. Review and correct accordingly.
8 | Callout | 5 | alexis.martinez | Page 5. The size of Nozzles 11N A-H looks small. Base on TAM-EF-878 the minimum size is 1". Review and correct accordingly.