## 050-D-GAD-55001-001-RB
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Ahmed.Marhoon | JV replies on comments related to instrumentation and control scope in previous revision need to be discussed with the concerned personnel at the MOC for mutual agreement on way forward.
2 | Callout | 1 | alexis.martinez | Review the size of 2M Nozzle. The size in Revision A, is 32" diameter which also is shown in GD-D1285
3 | Callout | 1 | alexis.martinez | Review the size of Nozzles 11N A-H. Based on TAM-EF-878 the minimum size is 1".