## 050-D-GAD-55002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Yousif Ahmadi | 100% per FEED datasheet
2 | Callout | 1 | Erwin.Lugue | To include in brackets load values in metric units
3 | Callout | 1 | Abdul Rahim | refer to all comments as for 050D0001
4 | Call-out | 1 | MAK | Change to 050D1002. All tag nos. shall be as per the agreed and final equipment lists.
5 | Text Box | 1 | MAK | General Comment: The latest drawing borders have been submitted to JV Directorate on April 2018. Please use the latest drawing borders that are part of the Homogenisation Procedure.
6 | Callout | 1 | Erwin.Lugue | To include in brackets load values in metric units. Calculations of wind loads shall be as per the approved code in the basis of design
7 | Text Box | 1 | MAK | General Comment: Texts font style and size shall not be changed. Every drawing border is predefined with font style and size.