## 050-D-GAD-55002-004-RB
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Robert.Kawitzki | Add walkways when nozzle orientation has been finalized as per BMPS A5