## 050-D-GAD-55003-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | General Comment: The latest drawing borders have been submitted to JV Directorate on April 2018. Please use the latest drawing borders that are part of the Homogenisation Procedure.
2 | Text Box | 1 | MAK | General Comment: Texts font style and size shall not be changed. Every drawing border is predefined with font style and size.
3 | Callout | 1 | Abdul Rahim | confirm requirement
4 | Call-out | 1 | Edgardo | This drawing title does not reflect the contents of all the pages for this drawing number. As an example, Sheet 3 is showing the elevation view
5 | Text Box | 1 | Ahmed Marhoon | Size of nozzles for the temperature gauges to be verified/confirmed by contractor with respect to BMPS-J2 and BMPS typical drawings (4 inch Vs 1.5 inc).
6 | Callout | 1 | Erwin.Lugue | To include in brackets load values in metric units. Calculation of the wind loads shall be as per the approved code in the basis of design
7 | Call-out | 1 | Ahmed Marhoon | Per P&ID, three independent nozzles are required for the temperature gauges at different elevations. Nozzle schedule to be updated accordingly.
8 | Callout | 1 | Yousif Ahmadi | 19.05 mm per FEED data sheet. check and confirm
9 | Text Box | 1 | Ahmed Marhoon | Contractor to cross check the instrument nozzles with the P&ID and ensure consistency. e.g. number of level transmitters is not matching with P&ID.
10 | Text Box | 1 | Ahmed Marhoon | Details of the level and temperature instruments nozzles (including stilling well) to be updated based on the latest standard drawing. Refer to comment on note 22 on sheet 2 of this GAD.
11 | Callout | 1 | Yousif Ahmadi | 100% per FEED datasheet
12 | Call-out | 1 | MAK | Change to 050D1003. All tag nos. shall be as per the agreed and final equipment lists.
13 | Call-out | 1 | Ahmed Marhoon | Comments on GAD-55003-001, 002, 003 and 004 of tank 050D0003 are also applicable for GADs of tank 050D0004.
14 | Callout | 1 | Yousif Ahmadi | A 573 Gr 70/A36/A 105
15 | Callout | 1 | Erwin.Lugue | Units shall be in S.I.
16 | Callout | 1 | Abdul Rahim | add viscosity and pour point at operating temperature for vacuum resid
17 | Callout | 1 | Erwin.Lugue | To include in brackets load values in metric units